## Dashboard
QDD Actuator — Project Dashboard
Requirements Summary
Total Requirements | 13
Verified | 0
Failed | 2
Partial | 1
Pending Review | 2
Not Verified | 8
% Verified | 0%
Test Campaign Summary
Total Tests | 19
Complete | 5
In Progress | 0
Not Started | 14
Pass | 1
Fail | 2
% Complete | 26.32%
Traceability Coverage
Covered (Primary Test) | 2
Partial (Secondary Only) | 4
Via Inspection/Demo/Analysis | 5
Gap (No Coverage) | 2
Gap Req IDs | R-07, R-08
Unknowns Register
Total Unknowns | 10
Resolved | 1
Open (excl. Merged) | 8
% Resolved | 11.11%

## Requirements
Req ID | Requirement | Description | Target Value | Type | Priority Rank | Verification Method | Status | Verified By | Notes
R-01 | Backlash | Angular backlash at output shaft | ≤ 0.5° | Hard | 1 | Test | Partial | T-012 | Primary QDD metric. Measured with dial indicator.
R-02 | Cost | Total BOM cost under budget | < $120 CAD | Hard | 2 | Inspection | Pending Review | BOM inspection | Sum of purchased + printed parts cost
R-03 | DFM/DFA | All off-the-shelf + 3D printed parts; assemblable without complex tools | Off-the-shelf + FDM, no special tools | Hard | 3 | Inspection | Pending Review | Design review | Assembly with basic hex keys only
R-04 | Backdrivability | Friction torque with motor disconnected | < 1 Nm friction torque | Hard | 4 | Test | Failed | T-013, T-008, T-006 | Changed from vague 'backdriveable under human impulse' to measurable spec (Mar 11). Industry standard for QDD.
R-05 | Durability | Should not break itself in under 1 minute | No self-destruction in < 1 min | Hard | 5 | Test | Not Verified |  | Phase 5 only. Combination of software + hardware limits.
R-06 | Peak Torque | Peak torque output at gearbox output shaft | ≥ 16 Nm | Hard | 6 | Test | Not Verified |  | Phase 5 only. Needs load cell or heavy weights.
R-07 | Continuous Torque | Sustained torque output capacity | ≥ 12 Nm | Hard | 7 | Test | Not Verified |  | Phase 5 only. Needs thermal steady-state test.
R-08 | Thermal Performance | Housing should not overheat under sustained use | No melting in < 5 min | Hard | 8 | Test | Not Verified |  | Phase 5 only. PLA Tg ~60°C. Health monitoring tracks informally.
R-09 | Efficiency | Power transmission efficiency through gearbox | > 90% | Soft | 9 | Test | Failed | T-006 (related) | Phase 5 only. T-006 measures friction but not output power directly.
R-10 | Weight | Total assembly mass | < 2 kg | Soft | 10 | Inspection | Not Verified |  | Trivial — kitchen scale measurement. Add as 1-min check in Phase 1.
R-11 | Speed | Maximum continuous output RPM | ≥ 600 RPM continuous | Soft | 11 | Test | Not Verified | T-016 (related) | T-016 measures bandwidth, not sustained max RPM. No direct 600 RPM test yet.
R-12 | Integratable | Support either shaft or bolted plate outputs | Shafts or bolted plates | Soft | 12 | Demonstration | Not Verified |  | Design review / demo of integration options.
R-13 | Torque Density (volume) | High torque output relative to actuator volume | No specific target set | Soft | 13 | Analysis | Not Verified |  | Compare to commercial QDDs (e.g., CubeMars AK70-10).

## Traceability Matrix
|  | Ph0 | Ph0 | Ph0 | Ph0 | Ph1 | Ph1 | Ph2 | Ph2 | Ph2 | Ph3 | Ph3 | Ph4 | Ph4 | Ph4 | 00A | 00A | 00A | 00A | 00A
Req ID | Requirement | T-009 Motor Kt | T-010 Motor Cogging | T-011 Motor Friction | T-014 Motor Step Resp | T-012 Backlash | T-013 Hand Backdrive | T-006 Friction Model | T-007 Step Response | T-008 Backdrive Torque | T-015 Plant ID | T-016 Bode Plot | T-017 Virtual Spring | T-018 Spring-Damper | T-019 Variable Imped | T-001 Root Cause Mesh | T-002 Lid Drag | T-003 Shoulder Deform | T-004 Carrier Index | T-005 Bolt vs Drag | Coverage
R-01 | Backlash |  |  |  |  | P | [9 empty] | S |  |  | S |  | Covered
R-02 | Cost | [19 empty] | Via Inspection
R-03 | DFM/DFA | [19 empty] | Via Inspection
R-04 | Backdrivability | [5 empty] | P | P |  | P | [5 empty] | S | S |  |  | S | Covered
R-05 | Durability | [16 empty] | S |  | S | Partial
R-06 | Peak Torque | [16 empty] | S |  | S | Partial
R-07 | Continuous Torque | [19 empty] | Gap
R-08 | Thermal Performance | [19 empty] | Gap
R-09 | Efficiency |  |  | S |  |  |  | S | [12 empty] | Partial
R-10 | Weight | [19 empty] | Via Inspection
R-11 | Speed | [10 empty] | S | [8 empty] | Partial
R-12 | Integratable | [19 empty] | Via Demonstration
R-13 | Torque Density (volume) | [19 empty] | Via Analysis
| Traces To → | Char. | Char. | R-09 | Char. | R-01 | R-04 | R-04, R-09 | Char. | R-04 | Char. | R-11 | Char. | Char. | Char. | R-01, R-04 | R-04 | R-05, R-06 | R-01 | R-04, R-05, R-06
Legend
P | Primary verification test
S | Secondary / supporting test
No direct link
Char. | Characterization test (no specific req)

## Test Log
Test ID | Test Name | Phase | Traces To | Procedure Reference | Prerequisites | Status | Date Executed | Result | Acceptance Criteria | Pass/Fail | Notes / Actions | Trace Valid?
T-001 | Root cause analysis — tight gear meshing | Rev 00A | R-01, R-04 | test-tracker.md T-001 | Part dimensions | Complete | 2026-03-13 | Herringbone alignment error identified | Dimensions within printer tolerance | Partial | Root cause: herringbone misalignment. Action: spur gears for Rev 00B. Dimensional measurements still pending. | ✓
T-002 | Lid drag — over-constraint on carrier | Rev 00A | R-04, R-09 | test-tracker.md T-002 | None | Complete | 2026-03-13 | Root cause identified — tolerance stackup | Lid does not add parasitic drag | Fail | Lid double-duty causes stackup. Design change: decouple ring gear clamping from carrier constraint. | ✓
T-003 | Carrier bearing shoulder deformation | Rev 00A | R-05, R-06 | test-tracker.md T-003 | None | Complete | 2026-03-13 | Print quality issue on top carrier shoulders | Shoulder change < 0.1 mm, no cracking | Inconclusive | Bottom shoulders good. Top shoulders have print artifacts (orientation trade-off). No dimensional measurement yet. | ✓
T-004 | Carrier half indexing — clocking under load | Rev 00A | R-01 | test-tracker.md T-004 | T-003 | Complete | 2026-03-13 | ~0.5 mm play exists but no operational driving force | No visible relative motion under hand torsion | Pass | Load path analysis: both halves driven by same pins. Clocking not a realistic failure mode. | ✓
T-005 | Carrier bolt torque vs planet resistance | Rev 00A | R-04, R-05 | test-tracker.md T-005 | None | Complete | 2026-03-13 | Narrow window between carrier play and planet binding | Planets spin freely across bolt torque range | Fail | Shoulders sensitive to clamping force. 1.1 Nm → drag. Backed off → free. Rev 00B shoulder redesign needed. | ✓
T-006 | Friction characterization — Coulomb + viscous | Phase 2 | R-04, R-09 | test-campaign-rev00b.md Phase 2 | Motor + encoder + ODrive, gearbox assembled | Not Started |  |  | Reflected friction torque < 1 Nm; linear friction model |  | Motor torque current at constant velocities. Subtract T-011 baseline for gearbox-only friction. | ✓
T-007 | Step response — system dynamics | Phase 2 | — | test-campaign-rev00b.md Phase 2 | Motor + encoder + ODrive, gearbox assembled | Not Started |  |  | System settles, overshoot < 10%, SSE < 0.5° |  | Characterization test. Compare to T-014 motor-only baseline. | N/A
T-008 | Backdriving torque — passive resistance | Phase 2 | R-04 | test-campaign-rev00b.md Phase 2 | Motor + encoder + ODrive, gearbox assembled | Not Started |  |  | Backdriving torque < 1 Nm at output |  | Quantitative version of T-013. Motor in idle, turn output by hand. | ✓
T-009 | Motor Kt verification (baseline) | Phase 0 | — | test-campaign-rev00b.md Phase 0 | ODrive + motor + encoder configured | Not Started |  |  | No-load Iq < 1A at 2 rev/s |  | Baseline sanity check. Every downstream torque calc depends on Kt. | N/A
T-010 | Motor cogging & friction profile | Phase 0 | — | test-campaign-rev00b.md Phase 0 | T-009 pass | Not Started |  |  | Periodic cogging, roughly symmetric CW/CCW |  | Motor-only baseline. Needed to isolate gearbox effects in T-006. | N/A
T-011 | Motor friction vs speed — no load | Phase 0 | — | test-campaign-rev00b.md Phase 0 | T-009 pass | Not Started |  |  | Roughly linear friction vs speed |  | Motor-only Coulomb + viscous model. Baseline for T-006 subtraction. | N/A
T-012 | Output shaft backlash measurement | Phase 1 | R-01 | test-campaign-rev00b.md Phase 1 | Gearbox assembled, motor shaft locked | Not Started |  |  | Backlash ≤ 0.5° (R-01 hard req) |  | Dial indicator + lever arm at 4+ positions around one revolution. | ✓
T-013 | Hand backdriving — qualitative + rough torque | Phase 1 | R-04 | test-campaign-rev00b.md Phase 1 | Gearbox assembled | Not Started |  |  | Backdriving torque < 1 Nm (R-04) |  | Kitchen scale + 200 mm lever arm. Quick check before powered T-008. | ✓
T-014 | Motor step response (baseline) | Phase 0 | — | test-campaign-rev00b.md Phase 0 | T-009 pass | Not Started |  |  | Clean second-order response, consistent across 3–5 reps |  | Motor-only baseline for T-007 comparison. Extract tr, OS%, ts, SSE. | N/A
T-015 | Plant identification from step response data | Phase 3 | — | test-campaign-rev00b.md Phase 3 | T-014, T-007 complete | Not Started |  |  | Model matches measured step response within 10% |  | Fit G(s) = 1/(Js² + bs). Use torque mode for open-loop plant ID. | N/A
T-016 | Frequency response — Bode plot | Phase 3 | — | test-campaign-rev00b.md Phase 3 | T-015 (for validation) | Not Started |  |  | Measured Bode matches predicted from T-015 |  | Chirp or discrete sine dwell. Motor alone AND motor+gearbox overlay. | N/A
T-017 | Impedance control — virtual spring | Phase 4 | — | test-campaign-rev00b.md Phase 4 | T-015 (plant model for tuning) | Not Started |  |  | Linear force-displacement, smooth feel, returns to setpoint |  | Tier A: use ODrive internal PID as spring-damper. Start here. | N/A
T-018 | Impedance control — spring-damper | Phase 4 | — | test-campaign-rev00b.md Phase 4 | T-017 | Not Started |  |  | Damped return to setpoint, higher K achievable with B |  | Tier B: Python torque loop (~200 Hz). True impedance control. | N/A
T-019 | Variable impedance demo (stretch goal) | Phase 4 | — | test-campaign-rev00b.md Phase 4 | T-018 | Not Started |  |  | Smooth real-time parameter adjustment, no instability |  | Tkinter GUI with K/B sliders. Portfolio hero content. | N/A

## Unknowns Register
Unknown ID | Description | Category | Priority | Status | Linked Tests | Resolution | Date Resolved
U-01 | Planet positioning & mesh clearance — geometry vs. assembly? | Assembly/fit | Test first | Postponed → Rev 00B | T-001 | Herringbone misalignment identified as root cause. Switched to spur gears.
U-02 | (Merged into U-01) | — | — | Merged
U-03 | Lid causing drag — over-constraint on carrier? | Assembly/fit | Test first | Root cause identified | T-002 | Tolerance stackup across carrier assembly causes lid to press on carrier top. Redesign for Rev 00B. | 2026-03-13
U-04 | Carrier bearing shoulder deformation under bolt torque | Structural | Test first | Confirmed | T-003, T-005 | Shoulders sensitive to torque. Print quality issue on top carrier. Rev 00B redesign. | 2026-03-13
U-05 | Carrier halves need indexing? | Assembly/fit | Monitor/skip | Resolved | T-004 | No operational clocking load — both halves driven by same pins. | 2026-03-13
U-06 | Gearbox structural capacity (handles motor torque × 5:1?) | Structural | After fundamentals | Not Started
U-07 | Output shaft strength — self-tap holding, diameter adequate | Structural | Verify early | Known Issue |  | Known undersized → enlarged in Rev 00B design.
U-08 | Backlash — quantified | Performance | After fundamentals | Not Started | T-012
U-09 | Backdrivability — quantified | Performance | After fundamentals | Not Started | T-013, T-006, T-008
U-10 | Durability under sustained use | Degradation | After fundamentals | Not Started

## Health Log
Date | Session # | Backlash (°) | Friction Torque (Nm) | Ambient Temp (°C) | Visual Condition | Cumulative Runtime (min) | Notes
| 1 |  |  |  |  | 0 | Initial baseline — record before first powered test

## Change Log
# | Change | Sheet(s) Affected | Details
1 | Data validation dropdowns added | Requirements, Test Log, Unknowns Register | Dropdowns on: Test Status (G), Pass/Fail (K), Req Type (E), Verification Method (G), Req Status (H), Unknown Status (E), Unknown Priority (D). Prevents typos, enforces consistent values.
2 | Coverage column auto-derived via formula | Traceability Matrix | V3:V15 now uses COUNTIF to detect P/S entries + MATCH to Requirements verification method. Conditional formatting: green=Covered, yellow=Partial, blue=Via Inspection/Demo/Analysis, red=Gap.
3 | Requirements Status auto-derived from Test Log | Requirements | H2:H14 formulas use SUMPRODUCT+SEARCH to look up linked test results. Statuses: Verified, Failed, Partial, Pending Review, Not Verified. Conditional formatting applied.
4 | Dashboard summary sheet created | Dashboard (new) | Formula-driven summary: Requirements status counts, Test campaign progress, Traceability coverage counts + gap Req IDs, Unknowns resolution status. All auto-update.
5 | Cross-reference validation column added | Test Log | Column M 'Trace Valid?' checks that Req IDs in 'Traces To' (col D) exist in Requirements!A:A. Shows ✓, ✗ Check IDs, or N/A for characterization tests.
6 | Color legend added to Traceability Matrix | Traceability Matrix | Legend in A18:B22 documents P (blue, primary), S (green, secondary), blank (no link), Char. (characterization).
7 | Health Log template improved | Health Log | Visual Condition dropdown added (Good → Needs repair). Session # auto-increments when Date is entered (B3:B50 formula). Placeholder styling cleaned up.